Annex 2: ASEAN Cooperation Project Proposal

For assistance on how to complete this template, please refer to the “ASEAN Cooperation Projects Design and Management Manual,” which can be downloaded at https://asean.org/wp-content/uploads/ASEAN-Cooperation-Projects-Design-and-Management-Manual.pdf. Proponent shall use Arial 11 font in the project proposal.

- PROJECT DETAILS

Proposal Identification Code: (to be completed by the ASEAN Secretariat)

Project Title: Technical Assistance for Project Development and Preparation for Smart and Sustainable Urbanisation in ASEAN Cities - Phase One

Write a short title that shows the main goal and objective of the project.

Brief Project description – 300 words max:

Provide a brief description of the project. It should be clear and brief and detail how it will contribute to ASEAN’s overall goals. Include: a) the objective/s (outcome/s), expected results (outputs), key activities, and how it will address the identified problem, b) the direct beneficiaries, and c) intended duration. If it is a Recurring or Next Phase project, explain briefly how it builds on the previous project.

Recognising the need to strengthen capacity for the local government and stakeholders to address urban challenges, it is essential to develop a comprehensive capacity building programme to assist cities in ASEAN in developing concrete action plans with financially viable project proposals. This Project is expected to enable ASEAN participating cities to tap technical assistance and financing, and commence implementation of projects. This will be achieved through the following main activities:

- Inception report;

- Development of City Diagnostic Reports;

- Development of City Technical Proposals/Documents;

- Seminars and Events.

Is this a Recurring project: Yes ☐ No ☒

If Yes, Previous Project Identification Code:

Recurring projects are repeated at regular or irregular intervals with the same or similar objectives (outcomes), outputs, and activities.

Is this a Next-Phase project: Yes ☐ No ☒

Next-Phase projects continue previous projects, either by expansion or incorporating additional areas, not covered or explored by the previous project.

Project Classification:

- Alignment to ASEAN Priorities

To determine the Project Proposal’s alignment to ASEAN priorities, please refer to Chapters 2 and 4 of the ASEAN Cooperation Projects Design and Management Manual and/or the ASEAN website for relevant guiding documents. Proponents can also consult with the ASEAN Secretariat.

Scope:			Single Sector ☒	Cross-Sector ☐

| Strategic Plan | APSC ☐ | AEC ☐ | ASCC ☒ |
| --- | --- | --- | --- |
| Strategic Goals: |  |  | 5. A Community where its peoples play an active role in all aspects of life through the promotion of human security, enhancing peoples’ resilience through public private partnerships in line with the ASEAN sustainability agenda. 12. A green ASEAN that will be achieved through sustainable growth on land and in water, as we embrace the green economy and blue economy in the regional context and strengthen ASEAN’s position in promoting sustainability and climate responses. |
| Objectives: |  |  | 5.1. To achieve an inclusive Community where all people have an active role to play in all aspects of life and achieve sustainable progress, including through partnerships and collaboration 12.1. To achieve a sustainable community that advances ASEAN’s sustainability agenda in coherence with the Sustainable Development Goals and the post-2030 global development agenda. |
| Strategic Measures: |  |  | 5.1.4. Strengthen local institutions and community-based approaches that promote the participation of local governments/ authorities, provinces, townships, municipalities, cities, and villages through the central government in the development of ASEAN capacity-building programmes that benefit their respective communities. 12.2.1. Implement a comprehensive strategy for sustainable urbanisation in ASEAN by enhancing participatory and integrated approaches in urban planning and management and strengthening the capacity of national and local institutions to effectively implement strategies and programs aimed at creating cities that are clean, green, liveable and enhance well-being. |

ASEAN Connectivity ☒ 	 			   IAI ☐

| Strategic Goal: 2. A Community capable of managing urban and rural challenges by leveraging modern technologies, and innovative infrastructure, as well as enhancing ASEAN smart and sustainable cities and villages. Objectives: 1. Advanced smart and sustainable urban and rural development. Strategic Measures: 2.1. Promote integrated, data-driven, and adaptive approaches to urban and rural planning. 2.3. Strengthen public safety and security in cities. 2.6. Strengthen existing urban and rural infrastructure, human resources, and knowledge sharing platforms to facilitate mobility, improve the efficiency and sustainability of building and construction, integrate effective land use planning, and build climate and disaster resilience, and disability-inclusive infrastructure for sustainable development. 2.7. Encourage industries and businesses to capitalise on technologies and use innovation to build competitive advantages and transform process. 2.12. Strengthen urban-rural linkages and spatial planning collaboration for sustainable urbanisation and sustainable community development. | Strategic Area: Objective: Actions: Enabling Actions: |
| --- | --- |

- Project type

To determine the project type, please refer to Chapter 4 of the ASEAN Cooperation Projects Design and Management Manual, or consult with the ASEAN Secretariat. There can be more than one type, but please indicate the predominant type based on the project objectives. If you select “Others”, please specify the nature of the project.

Primary Project type: 			______________________________________

| ☐ Awareness Raising/Public Outreach (e.g., forum, seminar, knowledge sharing, outreach and/or communication materials/activity, etc.) | ☒ Capacity Building (e.g., workshop, training, exchange, scholarship, technical assistance, special assistance, etc.) |
| --- | --- |
| ☐ Research and Analysis/Evidence Building (e.g., survey, research, baseline study, benchmarking, assessment, evaluation, review of strategic plans, etc.) ☐ Groundwork (e.g., new manual, innovative practices, business incubation model, invention of improved/new methods, use/introduction of new technology, strategy documents, etc.) | ☐ Policy-Related (e.g., harmonisation of national policies and institutional mechanisms, development and/or implementation of regional frameworks, establishment and/or operationalisation of regional mechanisms, policy dialogue, etc.) ☐ Pilot Implementation (Small-scale or localised implementation to test ASEAN-level policies, tools, technologies or models before scaling up.) |
| ☐ Others ____________________________________________________________ |  |

- Project duration:

Project duration is from the proposed commencement date to the end of implementation date. The actual commencement date is when the Implementing Agency/Proponent is informed by letter that the project is approved and receives the first payment. The end of implementation date is when the last activity outputs are finished. The project duration must match the implementation period in the work plan and budget. The Implementing Agency/Proponent must submit an updated work plan and budget (if applicable) within 30 days of starting the project to reflect the actual commencement date, approved budget, and any schedule changes.

<18 months ☒	18-30 months ☐ 	> 30 months ☒

Note: Modify the above table to show the start and end dates and close the Worksheet when you are done; it will calculate the dates and project duration.

- Participating ASEAN Member States:  	All ☒ 		Not all ☐

If not all (or not all in the same way), please indicate reason:

ASEAN cooperation projects are expected to involve the participation of every ASEAN Member State. If the States’ participation is in different ways (e.g., through different levels of assistance) or does not involve every State, please indicate the reason.

ASEAN Sponsoring Body

To determine the Sponsoring ASEAN Body, please refer to Annex 1 of the ASEAN Cooperation Projects Design and Management Manual, or consult with the ASEAN Secretariat.

Sectoral Committee/Main Body: ASEAN Smart Cities Network

Meeting Number/Date:   			dd/mm/yyyy

Working Group/Sub-Committee:

Meeting Number/Date:   			dd/mm/yyyy

Proponent’s name and address:

Contact Person and Details:

ASEAN Connectivity Division, ASEAN Secretariat

Implementing Agency’s name and address (if different from above):

Contact Person and Details:

China Center for Urban Development (CCUD), National Development and Reform Commission, China

Guohong Building C Block, No. 11, Muxidi Beili, Xicheng District, Beijing, China

Project Manager, Smart and Low Carbon Development Division

Ms.ZHAO Fan Fan

Cell: +86 18911528285

zhaofanfan@ccud.org.cn

Ms. Li De Fen

Director, Smart and Low Carbon Development Division

Cell: +86   13381115519

lidefen@ccud.org.cn

Colleagues from other agencies to be identified

Date of Proposal submission:  		February 2026

Proposed funding source(s):  Grant aid of the Chinese government

To determine the funding source, the Proponent can consult the ASEAN Secretariat, National Secretariat of their country, ASEAN Sectoral Committee, or ASEAN Body and Project Management Team (if available).

Proposed Project budget (total in USD): 2,893,544.01

<USD 1,000,000 ☐	>USD 1,000,000 ☒

Note: Projects above USD 1,000,000 will require independent/external evaluation.

To be completed by PCPMD, ASEAN Secretariat

Recommendation of the ASEAN Secretariat

Meeting No./Date:	dd/mm/yyyy

Action:			Endorsed ☐	Not Endorsed ☐

Approval of Committee of Permanent Representatives to ASEAN (CPR)

Meeting No./Date: 	dd/mm/yyyy

Action:			Endorsed ☐	Not Endorsed ☐

- PROJECT JUSTIFICATION, REGIONALITY, AND BENEFICIARIES

For assistance on filling out this section, please refer to Chapter 4 of the ASEAN Cooperation Projects Design and Management Manual and/or the ASEAN website for relevant guiding documents. Proponents can also consult the ASEAN Secretariat.

- Problem Statement: In up to 600 words, describe the problem/s in the region or sector that the project aims to address. Guiding points:

  - The regional problem(s) the project is trying to address

  - Underlying causes of the problem

  - Supporting data or evidence to establish the problem’s existence.

Cities are often faced with challenges in mobilising requisite financing for smart and sustainable urbanisation projects. Some of these challenges include: properly prepared projects, national/local sovereign ceilings limiting the capacity to provide guarantees; debt service and repayment capacity; and legislative limitations.   There is also a lack of capacity to utilise the appropriate financing and commercial structures for city projects. Common hurdles relating to stakeholder understanding, trust, regulations, inclusion, procurement, economic models also need to be addressed in promoting and developing smart cities.

The ASEAN Smart Cities Network (ASCN) was established to provide a collaborative platform where cities work together towards the common goal of smart and sustainable urban development.  The ASCN aims to: (i) facilitate cooperation on smart cities development through sharing of best practices and developing action plans; (ii) catalyse viable projects with the support of the private sector and other solution providers; and (iii) encourage funding and support from ASEAN’s external partners and multilateral financial institutions.

The ASEAN Sustainable Urbanisation Strategy (ASUS), on the other hand, was launched at the 22nd ASEAN Coordinating Council (ACC) Meeting on 13 November 2018.  The ASUS comprises seven priority sub-areas and eight priority actions (Exhibit 1). Two accompanying toolkits have also been developed to assist cities in ASEAN to advance sustainable urbanisation, namely:

| Toolkit 1 Toolkit 2 | : : | Prioritising focus areas and actions for enhancing sustainable urbanisation; and Sustainable urbanisation action templates. |
| --- | --- | --- |

Through the ASCN platform, the ASCN develops synergies with ASEAN Sustainable Urbanisation Strategy, and strengthen smart city partnerships beyond the region.  Such collaborations can bring about more tangible outcomes by pooling together the knowledge, expertise and resources required.

The ASUS and its toolkits have been disseminated to city networks in ASEAN, such as the ASCN, the ASEAN Sustainable Development Goals (SDG) Frontrunner Cities Programme, and various other city networks in ASEAN, such as those operating under the Brunei Darussalam-Indonesia-Malaysia-Philippines – East ASEAN Growth Area (BIMP-EAGA), and the Indonesia-Malaysia-Thailand – Growth Triangle (IMT-GT). Cities can use and customise the ASUS toolkits into action plan templates/project proposals in the selected priority action(s) for their city context and based on their needs. Subsequently these templates can be used to develop viable project proposals to help engage ASEAN Dialogue Partners and Other External Partners, multilaterals, the private sector and other external partners for technical assistance and financing, and then to commence implementation.

However, one of the key challenges at the city level pertains to the lack of the resources or capacity within local government to customise the action plans to their specific context and mobilising financing. While some technical support is provided through the various city networks in ASEAN, further resources may be needed to help cities develop proposals that are ready to engage potential development and implementing partners. This is important to ensure that there is a strong pipeline of high-quality proposals emerging from these networks, with the requisite support to roll out the ASUS priority actions intended by cities.

Exhibit 1

- Regionality: To qualify as an ASEAN cooperation project, keep the following in mind:

  - Is the project addressing a regional problem?

  - Is the project proposing a regional intervention?

  - Does the project involve and/or benefit all ASEAN Member States?

  - Does the project complement and provide value-add to ASEAN Member States interventions at the national level?

Cities are at the frontline of key global trends and challenges affecting the region, from pandemic to climate change and digitalisation to inclusive growth. Pursuing smart and sustainable urbanisation in ASEAN can help cities to recover from and adapt to the current challenges and better prepare for future problems, whether these are internal or external, short-term or long-term, expected or unexpected. This is particularly related to the region’s recovery and build resilience. This is reflected in the implementation of the ASEAN Comprehensive Recovery Framework which highlights the importance of smart city and sustainable urbanisation development in the region’s recovery efforts. Smart and sustainable urbanisation has therefore become an important part of ASEAN’s efforts to raise the standards of living of its peoples and empower them to seize opportunities and tackle head on whatever challenges may arise in the coming years.

The COVID-19 pandemic had highlighted the promise and possibilities of smart and sustainable urbanisation. One key development is the need to use technology. Whether it is sustainable public transport options or low carbon technology solutions, innovation and technology will shape the future of cities in ASEAN.  With technology redefining what is possible for cities to achieve, it is essential to build the capacity and capability of the region’s human capital to seize this opportunity.

- Project History: List any related projects or activities, past or present, and explain how this new proposal complements them. For recurring or next-phase projects, include the results achieved, outputs and outcomes if available, lessons learned, and any evaluation reports from the previous project as annexes.

The 22nd ASEAN-China Summit in November 2019 adopted the ASEAN-China Leaders’ Statement on Smart City Cooperation Initiative, reaffirming both sides’ commitment to further explore science, technology and innovation (STI) cooperation and collaboration in areas of mutual interests, as well as to achieve innovation-driven development in areas such as smart city development. In ASEAN, smart cities and sustainable urbanisation are pursued through two key Initiatives, namely the ASCN and ASUS. Hence, this proposed project seeks to further operationalise the commitments expressed in the above-mentioned occasions.

There was an earlier version of the project proposal which was endorsed by the ASCN in November 2023. The endorsement was followed by the nomination of the following cities by ASEAN Member States in 2024:

- Sihanoukville City, Cambodia

- Sumedang, Indonesia

- Luang Prabang City, Lao PDR

- Cebu City, the Philippines

- Phuket, Thailand

The five cities have submitted their respective Letters of Intent and supporting information to the China Center for Urban Development (CCUD). The Letters of Intent and supporting information confirm the cities’ commitment to participating in the Project as well as outline their expectations on the Project. The budget and work plan appearing in Annex 1 and Annex 2, respectively, have been prepared for the Phase One of the Project.

- Beneficiaries:  State who and how many people will directly benefit from the project. This can include individuals, organisations, a specific ASEAN sector or ASEAN Member States. Where relevant, detail direct beneficiaries by gender, location, designation, organisation-type, sector, or socio-demographic profiles. Specifically indicate the number of male and female beneficiaries. The target number of beneficiaries is also linked to the project’s indicators. Proponents should also identify indirect beneficiaries.

| Types of beneficiaries | Details Provide details on beneficiaries’ (gender, location, designation, organisation type, etc) |
| --- | --- |
| Direct: | This project covers all ASEAN Member States (AMS) in advancing cooperation on smart cities and sustainable urbanisation development between ASEAN and China towards a more connected ASEAN region. National Representatives and Chief Smart City Officers of the ASCN, and relevant local authorities. |
| Indirect | People in the AMS will be the indirect beneficiaries of the project. Trained experts would be able to undertake smart city development and implementation more effectively in the region. This would improve and enhance the welfare of the ASEAN citizens. |

- PROJECT RESULTS

Use the table below to list the outputs needed to achieve each outcome. A project can have multiple outcomes and outputs, each with corresponding activities. Add rows and adjust numbering as necessary.

| Impact: The intended physical, financial, institutional, social, environmental, or other high-level development results, e.g., at the ASEAN Strategic Plan level, in line with the Project Classification’ section. Key question: What long term change does the project intend to achieve? Increased deployment of smart and sustainable urbanisation in ASEAN. |  |  |
| --- | --- | --- |
| Project Outcome The outcome is the final result of the project showing the intended changes, e.g., in practices or policies. A project usually has one main outcome but can have several intermediate outcomes, such as changes in target group actions, behaviours or relationships between stakeholders Key questions: - What results/changes does the project intend to achieve through its outputs and activities? - Who are the targeted beneficiaries or stakeholders? | Indicators An Indicator is a quantitative or qualitative factor or variable that shows how well an outcome or output has been achieved. Key questions: - How do we know the outcome is achieved? - How will achieving project outcome/output be measured? | Means of Verification (MOV) An MOV details where to get information to measure an indicator e.g., training reports, data sheets, before-and-after photos, etc. Key questions: - How will data be collected and reported? - What secondary sources are available? - Does the project use primary data collection tools? |
| Local governments of participating ASEAN cities acquired better knowledge and capability to further their smart and sustainable urban development efforts. | City diagnostic reports developed. City technical proposals/documents developed. | Local governments of participating ASEAN cities present to ASEAN on their experience in the development of their respective city technical proposals/documents. |
| Output 1 This is the direct or immediate product, service, or access produced/delivered by the project activities (e.g., individuals trained, workshops delivered, policy documents or knowledge products produced, etc). Outputs should be tangible, observable, and measurable. The IA is accountable for the outputs. | Indicators See above. Where applicable, please refer to the ASEAN Cooperation Projects Design and Management Manual Annex for the list of ASEAN Cooperation Project Standard Output Indicators. | Means of Verification See above. |
| Inception report to provide key stakeholders with clear understanding on the activities and outputs expected from this project. | Clarity of the approach, work plan, management plan, and budget allocation. | Review and feedback from ASEAN stakeholders on the draft inception report. Attendance list of the inception seminar. Report of the inception seminar. |
| Key Activities 1 A key activity is a specific action taken to achieve an output. Key question: What steps are needed to produce this output? Each activity should clearly connect to its output. - Outline of the overall approach, work plan, management plan and budget. - Conduct of a regional inception seminar (in-person) with all participating cities and relevant ASEAN stakeholders to: - foster peer-to-peer learning among participating cities; - discuss the approach work modality and focus areas for the city diagnostic exercise; - identify the focal point from each participating city to support the city diagnostic exercise and technical proposal/document development. - A city in AMS is the preferred location for the inception seminar; alternatively, consideration may be given to hosting in the same city where other high-level ASEAN-China meetings are taking place concurrently. - A launch event will be organized in conjunction with the inception seminar, featuring the attendance of high-level officials from ASEAN and China. |  |  |
| Output 2 | Indicators | Means of Verification |
| City diagnostic report for each participating city (one city per AMS). City diagnostic exercise aims to provide a better understanding of the city's context, strengths, and challenges in achieving smart and sustainable urbanisation, looking both at the overall context at the city-wide scale and then focusing on the selected project area. | Comprehensiveness and accuracy of review, assessment, and analysis in the city diagnostic reports on: - Key challenges for urban planning and management - Governance and institutional environment - Sectoral analysis - Alignment to global standards and impact - Recommendations for city technical proposals/documents | Review and feedback from ASEAN stakeholders on the draft city diagnostic reports. Attendance list of the regional knowledge-sharing and consultation exchange event. Report of the regional knowledge-sharing and consultation exchange event. Reports of the 1st and 2nd city consultations. |
| Key Activities 2 - Identification of expected key outputs & activities, key stakeholders, existing opportunities to leverage, potential risks to mitigate for each participating city. - Conduct of the 1st city consultation (online) for each participating city to gain an in-depth understanding of the development needs of cities and to provide concrete suggestions for the next work tasks. - Conduct of city diagnostic exercise for each participating city. - Collaborating and co-creating for better solutions with a “working backwards” approach - finding solutions from citizens' pain points rather than forcing solutions. - Conduct the 2nd city consultation (in-person) for each participating city with the relevant city stakeholders to review and verify the findings of the city diagnostic exercise. - Conduct of a regional knowledge-sharing and consultation exchange event (in-person), prior to the formation of the city technical proposals/documents, with all participating cities and relevant ASEAN stakeholders to: - share and exchange information on the review, assessment, analysis, and recommendations in the city diagnostic reports; - further discuss the outline of the city technical proposals/documents; - discuss the support needed to develop the city technical proposals/documents. |  |  |
| Output 3 | Indicators | Means of Verification |
| City technical proposal/document for each participating city (one city per AMS). Depending on the project/action proposed by the participating cities, the city technical proposals or city technical documents will be developed to support the smart city development across ASEAN. | Comprehensiveness and clarity of the city technical proposals/documents on: - Context and rationale - Scope and focus of the intervention - Intervention set-up and implementation - Intervention budget - Risk analysis - Monitoring and evaluation strategies. Relevance and acceptation of the city technical proposals/documents. | Review and feedback from ASEAN stakeholders on the draft city technical proposals/documents. Attendance list of the closing event. Report of the closing event. Attendance list of the 3rd city consultation (training). Report of the 3rd city consultation (training). |
| Key Activities 3 - Conduct of the 3rd city consultation (in-person) in the form of capacity building for city officials and hands-on trainings for development of technical proposal/document for each participating city. This includes a capacity building event to enhance the participating cities’ abilities in different fields of city development, to be determined by the cities’ interests and supported by the city diagnostic reports. - Convening of a closing event to: - release the final project outputs and share the results; - collect and analyse the participating cities' reflections and feedbacks on the project activities and processes; - understand the needs of the participating cities during and after the project; - provide opportunities for ASCN to exchange perspectives on the project with the participating cities; - discuss future plans taking into account project outcomes and lessons learnt. - The event will be held in the same city where other high-level ASEAN-China meetings are taking place concurrently. - The closing event will feature the attendance of high-level officials from ASEAN and China. |  |  |
| The project can have multiple outcomes or outputs. Add rows as necessary. |  |  |

- PROJECT MANAGEMENT ARRANGEMENTS

600 words max per section

- Management arrangements – Describe the project’s management structure, preferably through an organogram, including responsibilities, coordination mechanisms, and reporting lines. At a minimum, include the relevant ASEAN Bodies or Committees, ASEAN Secretariat, Project Team, Proponent, and Implementing Agency, and the external partner stakeholder, if applicable. Proponents can consult the Secretariat to identify other stakeholders. Reporting requirements should follow the guidance in the Disbursement Letter: progress reports for projects of 1-2 years, completion reports for all projects. If the IA has been identified, please describe their organisational capacity to implement and monitor this project, including past experience.

- Sponsoring Body

The ASCN will be the sponsoring and implementing body to provide technical perspective and guidance for project implementation and approving final results.

- ASEAN Secretariat (ASEC)

ASEAN Connectivity Division (ACD) will be responsible for the day-to-day management of the implementing agency and quality assurance of the deliverables. ACD will coordinate with relevant ASEC divisions and facilitate the consultation process with ASCN members.

- Implementing Agency

The implementing agency will be identified and be responsible for producing Outputs, including:

    - Plan all of the activities envisaged under each Output;

    - Carry out those activities with support from additional experts of other entities, industry, academia as needed;

    - Report the project outputs to ASCN and the Chinese Mission to ASEAN;

    - Consult with the relevant ASEAN sectoral bodies and stakeholders for successful implementation of the project;

    - Communicate the progress of Outputs to ASEC and the Chinese Mission to ASEAN.

- Human Resource inputs – Specify the type and number of personnel in the project, including terms of reference for each position, in the annexes, and any additional human resources, e.g., consultants.

Project team members including:

- ZHAO Fanfan, Assistant Research Fellow, China Center for Urban Development

- LI Defen, Director, Smart Low-Carbon Development, China Center for Urban Development

- WU Xiaomin, Research Group, China Center for Urban Development

- HUANG Xiying, Research Group, China Center for Urban Development

- LIU Peng, Research Group, China Center for Urban Development

- Additional researchers and assistants from CCUD and other competent partner agencies.

- Monitoring & Evaluation (M&E) – Briefly describe how the project will monitor and evaluate its intended results, and indicators, such as data collection, analysis, reporting, evaluation, and use of findings for feedback and learning. Include key M&E roles and responsibilities.

To determine what type of M&E and other performance measurements are required, please refer to the table below [to be deleted in the submitted/circulated proposal].

| Type of project | Required monitoring and evaluation |
| --- | --- |
| All types of projects | Progress monitoring (focus on activities implementation, outputs, and outcomes). Financial monitoring is advisable, and when required, shall follow SOP PFDR. |
| Project duration of 18 months or less | Final performance assessment and reporting (Project Completion Report) focus on the extent to which outputs and outcomes are achieved (fully, partially, or not achieved). |
| Project duration 18–30 months | Final evaluation upon completion of project. |
| Project duration of more than 30 months | Interim/midterm evaluation. Final evaluation upon completion of project. |
| Project budget of USD 1,000,000 or more | Independent evaluation at least once during the project. |
| Second or next phase of project with duration more than 18 months | Independent evaluation required before starting a new phase. |

The implementing agency will be responsible for monitoring and evaluating the project with the assistance and cooperation of ASEC. The progress will be reported accordingly to ASCN and the Chinese Mission to ASEAN.

The implementing agency will prepare and submit the project progress and interim financial reports to ASEC and the Chinese Mission to ASEAN with information regarding the progress which is made regarding the project’s implementation within 30 days after the end of 1st calendar year.

Moreover, the implementing agency will prepare and submit the project completion and final financial reports within 60 days of the project’s final activity being completed to ASEC and the Chinese Mission to ASEAN. The project completion report shall record the project achievements against the project’s original intended purpose, work plan, and outputs. It should assist in assessing impact, draw out conclusions and lessons learned that may be valuable in designing follow-on projects.

- PROJECT SUSTAINABILITY

300 words max

To fill out this section, please refer to Chapter 4 of the ASEAN Cooperation Projects Design and Management Manual, or consult the Secretariat. State how the outputs and benefits will be sustained after project completion. The project can include follow-up activities to help beneficiaries turn outputs into real benefits or outcomes.

The lack of resources and also capacity within local government to develop high-quality bankable project proposals and action plans is recognised as among the key challenges. Both institutional and technical capacity building of local governments participating ASEAN cities, as well as empowerment of people and communities in ASEAN cities are considered to be two essential measures or components which should be embedded in the workplan in order to guarantee the concrete ownership of project and programme achievements. A series of city consultations will be conducted and chaired by each local government itself in guiding the development of technical proposals/documents with support from local research institutes/agencies who can appreciate the unique context and challenges of each city.

Successful implementation of this project will require an integrated and holistic approach across all Outputs and their associated activities. In this sense, knowledge management is a special element of the project and will play a critical role in covering both capacity building for local authorities and stakeholders and broader dissemination of the project results. Knowledge management, especially knowledge transfer is crucial for scaling up of the project outcomes which are intended to be replicable. Such knowledge management will be carried out through development of each of the project outputs.

Depending on the recommendations arising from this project, a possible follow-on project could include city-to-city partnerships designed to connect ASEAN cities with their Chinese counterparts who are experiencing or have overcome similar challenges to their own and develop mutually beneficial solutions. This would allow knowledge transfer and ensure lasting impact.

- GENDER AND OTHER CROSS CUTTING ISSUES

300 words max

- Gender - Explain how the project will address gender issues; specifically addressing how women and men benefit equally. Indicate if resources are allocated for this purpose, how equal participation will be promoted, and how it will be monitored.

The project will take into consideration the need to enable participatory dialogues, plans and strategies that engage with varied stakeholders, at all levels. Gender balance will be sought in all the consultation processes during the project activities, as well as within information and knowledge sharing.

- Other cross cutting issues - State how cross-cutting issues will be addressed, such as:

- environmental sustainability

- inclusion of marginalised groups such as children, persons with disabilities, or elderly people

- human rights

- technology or social innovation and ICT issues.

As with the gender dimension, environment and social dimensions will be closely looked at during the implementation of project activities. For instance, gender, environment, and social dimensions will be analysed during the city diagnostic exercise to provide sound technical advice on how to integrate the cross-cutting issues to the city technical proposals/documents.

- Risk Mitigation

200 words max

Identify the main risks to achieving the project outcomes. Explain how you will reduce these risks, especially any social and environmental impacts. Fill in the two tables below with identified risks and mitigation strategies.

You may refer to Chapter 4 of the ASEAN Cooperation Projects Design and Management, or consult the ASEAN Secretariat.

Note: Risks are not certain but are reasonably likely to occur.

| Risk/Threat | Risk Mitigation Strategy |
| --- | --- |
| Negative factors that may impede or block achieving the outcomes, outside the control of the IA. | Strategy to reduce risks to achieving outcomes. |
| Differences of interest, commitment, and opinion or in understanding of a particular concern, especially between national government, local government, and partners. | - Ensure continuous dialogue and stakeholder engagement Work closely with designated focal points within city governments to ensure they are actively participated throughout the project. - Ensure continuous knowledge sharing |
| City authorities lack of data availability to develop the city diagnostic reports City authorities do not follow strategic advice and technical recommendations based on the city diagnostics. | - Apply appropriate city diagnostics tools to ensure that city project proposals/documents advance the implementation of smart and sustainable urban development - Provide sound technical advice on how to integrate the cross-cutting issues at project level |
| Local context is not mature enough for project bankability | - Ensure that the interventions are aligned and supported by national and municipal priorities and legal frameworks - Adapt interventions to the local context and ensure that they fulfil stakeholder expectations and needs |

Annex 1 – Budget Proposal

Use the provided template to list budgeted costs under the relevant headings. Base your budget on the resources needed for the Project Results (Section 3) and Project Management Arrangements (Section 5). Include a project evaluation budget if required.

Annex 2 – Indicative Work Plan

Use the provided template to develop a work plan with a timeframe for each project output and corresponding activities (Section 3), including M&E activities. The work plan must cover the entire project period (see note in the project duration section).

Annex 3 – Notation on Additional Supporting Documents

List supporting documents that will be submitted to help explain the proposal and its strategy, e.g., project reports, evaluation reports, or memoranda of understanding.

To be updated once the revised Manual is ready

To be updated once the revised Manual is ready

To be updated when  the new workplan is already launched [Initiative for ASEAN Integration (IAI) Work Plan V (2026-2030)]