## Sheet1
Approved by CPR through ad-referendum review and approval on 31 December 2025
Annex 2.2: Workplan Template
[Technical Assistance for Project Development and Preparation for Smart and Sustainable Urbanisation in ASEAN Cities]
China Center for Urban Development (CCUD), National Development and Reform Commission, China
June 2026 - May 2029
Outcome/Output | Planned Activities | Time-frame | [35 empty] | Budget (USD)
|  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year3
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Outcome 1 | [37 empty] | 2893544.01
Increased deployment of smart and sustainable urbanisation in ASEAN
Output 1
Inception report to provide key stakeholders with clear understanding on the activities and outputs expected from this project | Outline of the overall approach, work plan, management plan and budget. | bar: Year 1 1 to Year 1 2
An inception seminar will be held to discuss the work methods and focusing on areas for city diagnosis. | bar: Year 1 3 to Year 1 4
Output 2
City diagnostic reports for five recommended participating cities | Identification of expected key outputs & activities, key stakeholders, existing opportunities to leverage, potential risks to mitigate for each participating city. | bar: Year 1 5 to Year 2 2
City Consultation 1 will be held online. Participators include cities, respective national representatives, relevant city stakeholders familiar with local city development and ASEAN Secretariat. | bar: Year 1 7 to Year 1 10
Conduct of city diagnostic exercise for each participating city. | bar: Year 1 7 to Year 1 10
City Consultation 2 will be held seperately in each city. Participators include cities and their respective national representatives and relevant city stakeholders familiar with local city development. | bar: Year 1 11 to Year 2 2
A regional knowledge-sharing and consultation exchange event will be held to share and exchange information on the review, assessment, analysis, and recommendations in the city diagnostic reports; further discuss the outline of the city technical proposals/documents and the support needed to form the city technical proposals/documents. | bar: Year 2 3 to Year 2 4
Output 3
City technical proposals/documents for five participating cities | leverage on the city diagnostic reports and include context and rationale, scope and focus of the technical intervention, intervention set-up and implementation, intervention budget, risk analysis, and monitoring and evaluation strategies | bar: Year 2 5 to Year3 10
City Consultation 3 will be held offline as a training session. Participating cities with more than 1 bureau-level official, more than 5 department-level officials | bar: Year3 7 to Year3 10
The closing event will release the final output of the project and share the results, collect and analyse the feedback of the participating cities on the project; provide ASCN with the opportunity to exchange project views with the participating cities; and jointly discuss the future promotion plan. | bar: Year3 11 to Year3 12
Project Completion Report | bar: Year3 11 to Year3 12